## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING-PULBAZAR PUMPING-I PWSS | SM/18827 | New | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 51/NKWSMD | 09/01/2024 | 09/01/2024 | Resource Division | 22.53 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING-PULBAZAR PUMPING-I PWSS | SM/18827 | New | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all Civil, Electrical and Mechanical works like Intake, WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for Water Supply Scheme for Darjeeling Pulbazar Pumping - I Spring Water Supply Scheme followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000101/2024-2025 | 1567/NKWSMD | 03/09/2024 | 03/03/2026 | DARA ENGINEERING & INFRASTRUCTURES PRIVATE LIMITED | 15881.1 | 0 | 0 | 5
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING-PULBAZAR PUMPING-I PWSS | SM/18827 | New | (Continuation) Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate for the period from January 2025 to June 2025. | Assistant Engineer II | Junior Engineer II | ORD/000217/2024-2025 | 2412/NKWSMD | 31/12/2024 | 29/06/2025 | YAMA CONSTRUCTIONS LLP | 0.99 | 2.38 | 240.01 | 0
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | DARJEELING-PULBAZAR PUMPING-I PWSS | SM/18827 | New | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.05.2024 TO 31.08.2024. | Assistant Engineer II | Junior Engineer I | ORD/000001/2024-2025 | 779/NKWSMD | 30/04/2024 | 31/08/2024 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 0 | 100
Total | [13 empty] | 15905.41 | 2.38 | 0.01