## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | LOHAGARH WATER SUPPLY SCHEME | SM/09426 | New | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 637/NKWSMD | 23/02/2022 | 23/02/2022 | Resource Division | 2.36 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | LOHAGARH WATER SUPPLY SCHEME | SM/09426 | New | FOREST PAYMENT |  |  | BILL/00905/2023-2024 | BP-2023-24-497 | 17/02/2024 | 17/02/2024 | DIVISIONAL FOREST OFFICER | 7.43 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | LOHAGARH WATER SUPPLY SCHEME | SM/09426 | New | FOREST PAYMENT |  |  | BILL/00760/2023-2024 |  | 15/02/2024 | 15/02/2024 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | LOHAGARH WATER SUPPLY SCHEME | SM/09426 | New | LOHAGARH WATER SUPPLY SCHEME FROM MANAY KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DARJEELING |  |  | ORD/000069/2021-2022 | 459/NKWSMD | 14/01/2022 | 14/08/2028 | SHREE VAISHNO ENTERPRISES | 153.57 | 0 | 0 | 80
Total | [13 empty] | 174.08 | 0 | 0