## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RIMBICK WATER SUPPLY SCHEME | SM/09427 | New | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 1880/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 10.08 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RIMBICK WATER SUPPLY SCHEME | SM/09427 | New | Material Requisition To Resource Division |  |  | RTOR000163/2022-2023 | 2568/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 10.08 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RIMBICK WATER SUPPLY SCHEME | SM/09427 | New | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 1270/NKWSMD | 05/09/2022 | 05/09/2022 | Resource Division | 10.06 | 0 | 0 | 0
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | RIMBICK WATER SUPPLY SCHEME | SM/09427 | New | RIMBICK WATER SUPPLY SCHEME FROM PARTHAM KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DISTRICT-DARJEELING |  |  | ORD/000001/2022-2023 | 8/NKWSMD | 04/04/2022 | 01/10/2022 | NIMA SHERPA | 598.72 | 0 | 0 | 95
Total | [13 empty] | 628.93 | 0 | 0