## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Hatta Water Supply Scheme | SM/09449 | New | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 828/NKWSMD | 21/03/2022 |  | Resource Division | 1.9 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Hatta Water Supply Scheme | SM/09449 | New | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 1266/NKWSMD | 05/09/2022 |  | Resource Division | 1.91 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Hatta Water Supply Scheme | SM/09449 | New | HATTA WATER SUPPLY SCHEME FROM PAL MAJUA KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DISTRICT- DARJEELING. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000106/2021-2022 | 621/NKWSMD | 21/02/2022 | 21/07/2022 | HARI PRASAD CHETTRI | 303.02 | 271.97 | 89.75 | 100
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Hatta Water Supply Scheme | SM/09449 | New | Additional work for Hatta water supply scheme under Darjeeling Pulbazar Block, P.H.E. Dte. Darjeeling Division, G.T.A. |  |  | ORD/000245/2023-2024 | 1530/NKWSMD | 14/12/2023 | 12/02/2024 | MADAN KUMAR CHHETRI | 9.15 | 0 | 0 | 100
Total | [13 empty] | 315.98 | 271.97 | 86.07