## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Providing Functional Household Tap Connect ion under Jal Jeevan Mission and Jal Swapno Programme for Pipe Water Supply Sch eme for Pokhriabong Bazar from Nursery Fatak Source under Jorebanglow- Sukhiapokhri Block Darjeeling" |  |  | VCH/000063/2022-2023 | BP-2022-23-54 | 20/05/2022 | 20/05/2022 | RISHI KESH THAKURI | 7.36 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Providing Functional Household Tap Connection under Jal Jeevan M is si on.an d Jal Swapno Programme for Pipe Water Supply Sche me Scheme for 5th mile upper Kotwali Gaon. from Boka Jhora Source under Jorebanglow- Sukhiapokhri Block Darj eeling" |  |  | VCH/000055/2022-2023 | BP-2022-23-41 | 06/05/2022 | 06/05/2022 | KAMAKHYA ENTERPRISES | 3.63 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Providing Funct ional House hold Tap Connection under Jal Jeevan Mission an d Jal Swapno Programme for Pipe Water Supply Sc heme for Mazidhura Lower Parment Busty from Bhir Khola Sou rc e under Jorebanglow- Sukhiapokhri Block Darjeelin g under Darjeeling Division PH ED, GTA." |  |  | VCH/000156/2022-2023 | BP-2022-23-111 | 12/08/2022 | 12/08/2022 | KAMAKHYA ENTERPRISES | 3.68 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Providing Functional Household Tap Connection under Jal Jee van Mission and Jal Swapno Pro gramme for Pipe Water Supply Scheme for Lepcha Tribal Gaon Pokhriabong Busty from Gardinay Sim Source under Jorebanglow- Sukhiapokhri Block Darjeeling" |  |  | VCH/000284/2022-2023 | BP-2022-23-171 | 20/10/2022 | 20/10/2022 | RISHI KESH THAKURI | 3.13 | 0 | 0 | 0
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Providing Functional Household Tap Connection under JAL Jeeva n Mission and Jal Swapno Programme for Pipe Water Su pply Scheme for Chamong Maleteneya And Pari Gaon from Paa Khola and Kera Bari Source under Jorebangiow Sukhiapokhri Block Darjeeling" |  |  | VCH/000161/2022-2023 | BP-2022-23-105 | 08/08/2022 | 08/08/2022 | RISHI KESH THAKURI | 3.54 | 0 | 0 | 0
6 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Providing Functional Household Tap Conne ct ion under Jal Jee van Missi on and Jal Swapno Programme for Prpe Water Supply Sch eme for Tar zum under Jorebanglow Sukhiapokhri Block Darjeeling" |  |  | VCH/000112/2022-2023 | BP-2022-23-90 | 14/07/2022 | 14/07/2022 | SONAM TAMANG | 4.1 | 0 | 0 | 0
7 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Providing Functionai Household Tap Connection under Jal Jeevan Mission and Jal Swapno Pro grarnme for Pipe Water Supply Sch eme for Pokhriabong Busty No 4. from Ghimiray Jhora an Thulung Pakha Source under Jorebanglow - Sukhiapokhi" |  |  | VCH/000283/2022-2023 | BP-2022-23-170 | 20/10/2022 | 20/10/2022 | RISHI KESH THAKURI | 2.56 | 0 | 0 | 0
8 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Pipe Water Supply Scheme for Chotta Pubong ward No 3 & 4 from Singadevi Khela Source Under Jorebanglow - Su khiapokhri Block Dar je elin g under Darje eling Division PHED, GTA." |  |  | VCH/000068/2022-2023 | BP-2022-23-49 | 20/05/2022 | 20/05/2022 | KIRAN NIROLA | 3.11 | 0 | 0 | 0
9 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | "Jai Jeevan Mi ssion and Jal Swapno Programme for Pipe Water Su pply Scheme for Minzu Pussimbing from Bethany Khop Source under Jorebanglow Sukhiapokhri Block Darjeeling ." |  |  | VCH/000064/2022-2023 | BP-2022-23-53 | 20/05/2022 | 20/05/2022 | KESHAR CHETTRI | 4.91 | 0 | 0 | 0
10 | DARJEELING |  | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000001/2020-2021 | 123/EE/DD/PHED | 10/02/2021 | 10/02/2022 | SHREE VAISHNO ENTERPRISES | 110.23 | 4.36 | 3.96 | 0
11 | DARJEELING |  | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000003/2020-2021 | 123/EE/DD | 10/02/2021 | 22/03/2021 | SHREE VAISHNO ENTERPRISES | 40 | 14.68 | 36.69 | 0
12 | DARJEELING |  | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | Providing Functional Household Tap Connection under Jal jeevan Mission and Jal Swapno Programrne for Pipe Water Supply Scheme for upper Sirubari and Beech Gaon. Sungma T .E from Bara ReyangKhola Source under Jorebanglow Sukhiapokhri Block Darjeeling |  | Sub-Assistant Engineer | ORD/000004/2020-2021 | 114/EE/DD/PHED | 10/02/2021 | 10/06/2021 | SONAM TAMANG | 11.12 | 10.97 | 98.66 | 0
13 | DARJEELING |  | Darjeeling Division I | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (11 Nos.) under GTA. [Volume No-I] | SM/10259 | Retrofitting | Providing Fun ctional Household Tap Connection under Jal .Jeevan Mission and Jal Swapno Programme for Pipe Water Supp ly Scheme for Bhutia Gaon Plundung from Khodaydhura Khola Source unde r Jorebanglow- Sukhia.pokhri Block Darj eeling |  | Sub-Assistant Engineer | ORD/000002/2020-2021 | 117/EE/DD/PHED | 10/02/2021 | 10/06/2021 | ROMAN SHERPA | 3.69 | 3.55 | 96.38 | 0
Total | [13 empty] | 201.05 | 33.56 | 16.69