## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Kankeybong GP Lodhoma under Darjeellng Division PHED GTA" |  |  | VCH/000034/2022-2023 | BP-2022-23-34 | 20/04/2022 | 20/04/2022 | SACHIN PRADHAN | 13.66 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional Household d Tap Connection under JJM & JSP Programme for PWS Scheme for Lungtham Happy Valley under Darjeeling Division PHED GTA" |  |  | VCH/000035/2022-2023 | BP-2022-23-35 | 20/04/2022 | 20/04/2022 | SAMDEN DUKPA | 6.07 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Gairigoan Fatingtar GP Lodhoma II under Darjeeling Division PHED GTA |  |  | VCH/000024/2022-2023 | BP-2022-23-23 | 20/04/2022 | 20/04/2022 | BIRAJ RAI | 6.44 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional Household Tap Connecti on under JJM & JSP Pro gramme for PWS Scheme for Bijanbari Bazar GP Pull Bijnabari under Darjeeling Division PHED GTA" |  |  | VCH/000067/2022-2023 | BP-2022-23-52 | 20/05/2022 | 20/05/2022 | AROGYA ENTERPRISES | 24.75 | 0 | 0 | 0
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | Providing Functional Household Tap Connection und er JJM & JSP Programme for PWS Schem e for Lama goan GP Jhepi Kaijiliya under Darjeeling Division PHED GTA |  |  | VCH/000017/2022-2023 | BP-2022-23-16 | 11/04/2022 | 11/04/2022 | HARI PRASAD CHETTRI | 9.27 | 0 | 0 | 0
6 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Tukvar TG GP Tukvar under Darjeeling Division PHED GTA" |  |  | VCH/000066/2022-2023 | BP-2022-23-51 | 20/05/2022 | 20/05/2022 | VINAYAK CONSTRUCTION | 47.99 | 0 | 0 | 0
7 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Relling Bhibaray & Lr Relling GP Relling under Darjeeling Division PHED GTA" |  |  | VCH/000018/2022-2023 | BP-2022-23-17 | 11/04/2022 | 11/04/2022 | HARI PRASAD CHETTRI | 8.03 | 0 | 0 | 0
8 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Singhbhumdera GP Mazua under Darjeeling Division PHED GTA" |  |  | VCH/000023/2022-2023 | BP-2022-23-22 | 20/04/2022 | 20/04/2022 | KAMAKHYA ENTERPRISES | 13.75 | 0 | 0 | 0
9 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | Providing Functional Household Tap ·connection under JJM & JSP Programme for PWS Scheme for Samsu (Lower) Relling GP under Darjeeling Division PHED GTA |  |  | VCH/000028/2022-2023 | BP-2022-23-27 | 20/04/2022 | 20/04/2022 | KAMAKHYA ENTERPRISES | 4.03 | 0 | 0 | 0
10 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM &. .JSP Programme for PWSS Scheme for Dhotrey Forest fV GP Lodhoma 1 under DarJeeling Division PHED GTA" |  |  | VCH/000033/2022-2023 | BP-2022-23-33 | 20/04/2022 | 20/04/2022 | PASSANG TAMANG | 3.13 | 0 | 0 | 0
11 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 05/09/2022 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0 | 0
12 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional .Household Tap Connection under JJM & JSP Programme for PWS Scheme for Takbia (Lower ) GP Goke 1 under Darjeeling Division PHED GTA" |  |  | VCH/000036/2022-2023 | BP-2022-23-36 | 20/04/2022 | 20/04/2022 | SAILESH RAI | 7.3 | 0 | 0 | 0
13 | DARJEELING |  | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000001/2020-2021 | 123/EE/DD/PHED | 10/02/2021 | 10/02/2022 | SHREE VAISHNO ENTERPRISES | 110.23 | 43.08 | 39.08 | 0
14 | DARJEELING |  | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000003/2020-2021 | 123/EE/DD | 10/02/2021 | 22/03/2021 | SHREE VAISHNO ENTERPRISES | 40 | 10.01 | 25.03 | 0
15 | DARJEELING |  | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme Block-Darjeeling-Pull-Bijanbari, 11 Nos. existing schemes to be provided with FHTC under GTA. | SM/10260 | Retrofitting | "Providing Functional Household Tap Connection under JJM &. .JSP Programme for PWSS Scheme for Dhotrey Forest fV GP Lodhoma 1 under DarJeeling Division PHED GTA" |  | Sub-Assistant Engineer | ORD/000005/2020-2021 | 110/EE/DD/PHED | 10/02/2021 | 10/06/2021 | PASSANG TAMANG | 5.58 | 1.41 | 25.18 | 0
Total | [13 empty] | 373.7 | 54.5 | 14.58