## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. | SM/10261 | Retrofitting | Providing Functional household Tap Connection under JJM & JSP Programme for 8th & 9th M ile , Peshoke Road GP Lamahatta under DARJEELING Division PHED, GTA |  |  | VCH/000069/2022-2023 | BP-2022-23-50 | 20/05/2022 | 20/05/2022 | KIRAN NIROLA | 5.7 | 0 | 0 | 0
2 | DARJEELING |  | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. | SM/10261 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000001/2020-2021 | 123/EE/DD/PHED | 10/02/2021 | 10/02/2022 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0 | 0
3 | DARJEELING |  | Darjeeling Division I | Functional household tap connection under Jal Swapno Programme, Block-Rungli-Rungliot, 03 Nos. existing schemes to be provided with FHTC under GTA.. | SM/10261 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000003/2020-2021 | 123/EE/DD | 10/02/2021 | 22/03/2021 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0 | 0
Total | [13 empty] | 155.93 | 0 | 0