## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHALAMANSHI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15626 | Solarisation | Quotation Charges for Net Metering connection at Bhalamanshi Piped Water Supply Scheme under PHE Dte. Application no- 4003471161 Consumer ID- 402322812 |  |  | BILL/01062/2024-2025 | BP/24-25/167 | 29/08/2024 | 29/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
2 | DARJEELING |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT BHALAMANSHI PIPED WATER SUPPLY SCHEME UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15626 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | Assistant Engineer | Junior Engineer | ORD/000124/2023-2024 | 783/NMD | 14/07/2023 | 29/11/2025 | THE BUSINESS ENGINEERS INDIA | 87.64 | 0 | 0 | 90
Total | [13 empty] | 87.65 | 0 | 0