## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEM UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15854 | Solarisation | Solarisation of WBSEDCL Energised Electrical Installation at Paschim Madati and Others under Darjeeling District (Plains) under Northern Mechanical Division, P.H.E. Dte.. | Assistant Engineer | Junior Engineer | ORD/000124/2023-2024 | 783/NMD | 14/07/2023 | 29/11/2025 | THE BUSINESS ENGINEERS INDIA | 87.64 | 5.63 | 6.43 | 90
2 | DARJEELING |  | Northern Mechanical | SOLARISATION OF WBSEDCL ENERGISED ELECTRICAL INSTALLATION AT AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEM UNDER DARJEELING DISTRICT (PLAIN) UNDER NORTHERN MECHANICAL DIVISION, P.H.E. DTE. | SM/15854 | Solarisation | Quotation charges for Budharau Gaon PWSS. Application no : 4003651699 Consumer ID : 400650200 |  |  | BILL/00712/2025-2026 | 86/W/25-26 | 13/08/2025 | 13/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0 | 0
Total | [13 empty] | 87.65 | 5.63 | 6.43