## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Darjeeling & Kalimpong District of West Bengal. | SM/10538 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Darjeeling Hill Areas. | Assistant Engineer | Junior Engineer | ORD/000785/2022-2023 | 383/RS | 30/01/2023 | 28/07/2025 | DR AMIN CONTROLLERS PVT. LTD. | 193.59 | 142.3 | 73.51 | 20
2 | KALIMPONG |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Darjeeling & Kalimpong District of West Bengal. | SM/10538 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Darjeeling Hill Areas. | Assistant Engineer | Junior Engineer | ORD/000785/2022-2023 | 383/RS | 30/01/2023 | 28/07/2025 | DR AMIN CONTROLLERS PVT. LTD. | 193.59 | 142.3 | 73.51 | 20
3 | DARJEELING |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Darjeeling & Kalimpong District of West Bengal. | SM/10538 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Darjeeling Hill Areas. | Assistant Engineer | Junior Engineer | ORD/000058/2024-2025 | 1530/RS | 30/05/2024 | 24/12/2024 | DR AMIN CONTROLLERS PVT. LTD. | 84.37 | 84.06 | 99.63 | 25
4 | KALIMPONG |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Darjeeling & Kalimpong District of West Bengal. | SM/10538 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under Darjeeling Hill Areas. | Assistant Engineer | Junior Engineer | ORD/000058/2024-2025 | 1530/RS | 30/05/2024 | 24/12/2024 | DR AMIN CONTROLLERS PVT. LTD. | 84.37 | 84.06 | 99.63 | 25
5 | DARJEELING |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Darjeeling & Kalimpong District of West Bengal. | SM/10538 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under JJM in the State of West Bengal For 3(Three) Zone covering 6(Six) districts like Puraba Midnapore, Paschim Midnapore, Coochbehar, Alipurduar, Jalpaiguri, Uttar Dinajpur and Kalimpong against Zone VIII, ZONE III & Zone II repectively. |  |  | ORD/000131/2024-2025 | 2594/RS | 27/09/2024 | 27/11/2024 | TUV SUD SOUTH ASIA PVT. LTD. | 158.99 | 2.97 | 1.87 | 5
6 | KALIMPONG |  | Resource | Engagement of Third Party Inspection Agency (TPIA) for Quality and Quantity Monitoring of Rural Water Supply Schemes under JJM project in Darjeeling & Kalimpong District of West Bengal. | SM/10538 | Support-M&E | Quality and Quantity Monitoring BY Third Party Inspection Agency (TPIA) For Implementation Of Rural Water Supply Schemes under JJM in the State of West Bengal For 3(Three) Zone covering 6(Six) districts like Puraba Midnapore, Paschim Midnapore, Coochbehar, Alipurduar, Jalpaiguri, Uttar Dinajpur and Kalimpong against Zone VIII, ZONE III & Zone II repectively. |  |  | ORD/000131/2024-2025 | 2594/RS | 27/09/2024 | 27/11/2024 | TUV SUD SOUTH ASIA PVT. LTD. | 158.99 | 2.97 | 1.87 | 5
Total | [13 empty] | 873.9 | 458.65 | 52.48