## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000144/2022-2023 |  | 26/08/2022 | 26/08/2022 | SHREE VAISHNO ENTERPRISES | 14.05 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Khoprail sakha under Kurseong Sub-Division PHED. GTA |  |  | VCH/000155/2022-2023 | BP-2022-23-113 | 12/08/2022 | 12/08/2022 | CHARDHAM CONSTRUCTION | 3.83 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | Retrofitting | Providing Functional House hold Tap Connection under Jal Jeev an Mission and Jal Swapna Programme for Piped water Supply Scheme for Longview Tarai 34 & satt Ghurnt, St Mary's GP-Ill under Kurseong Sub-Division PHED. GTA. |  |  | VCH/000020/2022-2023 | BP-2022-23-19 | 20/04/2022 | 20/04/2022 | SURAJ LAMA | 6.2 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | Retrofitting | Providing Functional Household Tap Conne ction under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Mandir Busty, Giddhapa har underKurseong Sub-Division PHED, GTA |  |  | VCH/000159/2022-2023 | BP-2022-23-122 | 23/08/2022 | 23/08/2022 | NAVRATNA CONSTRUCTION CO | 6.08 | 0 | 0 | 0
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | Retrofitting | Providing Functional HouseholdTap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for for Hilay Jhora and Manju ak number Dara under Kurseong Sub-Division PHED, GTA |  |  | VCH/000154/2022-2023 | BP-2022-23-112 | 12/08/2022 | 12/08/2022 | CHARDHAM CONSTRUCTION | 3.7 | 0 | 0 | 0
6 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.) under GTA. [Volume No-II] | SM/10263 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 05/09/2022 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0 | 0
Total | [13 empty] | 107.33 | 0 | 0