## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | Retrofitting | Providing Functional Household Tap Connection unde.r Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Makaibari Tea Estate under Kurseong Sub-DIvision PHED, GTA |  |  | VCH/000022/2022-2023 | BP-2022-23-21 | 20/04/2022 | 20/04/2022 | NIPENDRA TAMANG | 10.07 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Selim Hill T .E.under Kurseong Division PHED), GTA |  |  | VCH/000014/2022-2023 | BP-2022-23-13 | 11/04/2022 | 11/04/2022 | SWAD CONSTRUCTION | 7.27 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sittong-1 & Sittong-111 under Kurseong Sub-Division PHED, GTA. |  |  | VCH/000026/2022-2023 | BP-2022-23-25 | 20/04/2022 | 20/04/2022 | BIKRAM RAI | 21.12 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 05/09/2022 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0 | 0
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Schem e for Dudhia Bazaar & its sorrounding area under Kurseong Sub-Division PHED, G1A |  |  | VCH/000037/2022-2023 | BP-2022-23-37 | 20/04/2022 | 20/04/2022 | SUN SHINE GROUP | 19.39 | 0 | 0 | 0
6 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme (5 Nos.). [Volume No-I] | SM/10264 | Retrofitting | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000143/2022-2023 |  | 26/08/2022 | 26/08/2022 | SHREE VAISHNO ENTERPRISES | 14.73 | 0 | 0 | 0
Total | [13 empty] | 146.04 | 0 | 0