## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. | SM/15650 | New | Material Requisition To Resource Division |  |  | RTOR000263/2022-2023 | 2777/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 1.44 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Gayabari Tea Garden with FHTC under JJM/JSP. | SM/15650 | New | WATER BASED GHAYABARI TEA GARDEN TO ACCOMODATE FHTC IN KURSEONG BLOCK |  |  | ORD/000325/2022-2023 | 2656/NKWSMD | 28/02/2023 | 27/08/2023 | ABHINAY CHETTRI | 200.32 | 0 | 0 | 100
Total | [13 empty] | 201.76 | 0 | 0