## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Selim Hill Tea Garden | SM/15652 | New | Material Requisition To Resource Division |  |  | RTOR000259/2022-2023 | 2771/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 2.37 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Selim Hill Tea Garden | SM/15652 | New | GRAVITY BASED WATER SUPPLYSCHEME FORUNDER SELIM HILL UNDER JAL JEEWAN MISSION |  |  | BILL/00398/2024-2025 | "BP-2024-25-289 | 24/09/2024 | 24/09/2024 | DIVISIONAL FOREST OFFICER | 3.2 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Selim Hill Tea Garden | SM/15652 | New | SURFACE WATER BASED SELIM HILL TEA GARDEN TO ACCOMODATE FHTC IN KURSEONG BLOCK |  |  | ORD/000341/2022-2023 | 2756/NKWSMD | 09/03/2023 | 08/03/2024 | SHAKTI CONSTRUCTION | 910.25 | 0 | 0 | 85
Total | [13 empty] | 915.81 | 0 | 0