## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS scheme for St. Mary's & Goethals | SM/15661 | New | Material Requisition To Resource Division |  |  | RTOR000258/2022-2023 | 2770/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 4.4 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS scheme for St. Mary's & Goethals | SM/15661 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS scheme for St. Mary's & Goethals | SM/15661 | New | PWS Scheme For St Marys and Geothals |  |  | BILL/00647/2024-2025 | BP-2024-25-458 | 09/12/2024 | 09/12/2024 | DIVISIONAL FOREST OFFICER | 2.52 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS scheme for St. Mary's & Goethals | SM/15661 | New | SURFACE WATER BASED ST. MARYS AND GOETHALS PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK. |  |  | ORD/000331/2022-2023 | 2670/NKWSMD | 01/03/2023 | 28/08/2023 | SITA SHARMA | 300.54 | 0 | 0 | 60
Total | [13 empty] | 356.72 | 0 | 0