## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | RANGMOHAN PIPED WATER SUPPLY SCHEME | SM/15880 | New | Material Requisition To Resource Division |  |  | RTOR000257/2022-2023 | 2776/NKWSMD | 10/03/2023 | 10/03/2023 | Resource Division | 1.06 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | RANGMOHAN PIPED WATER SUPPLY SCHEME | SM/15880 | New | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAMOHAN UNDER JAL JEEVAN MISSION. |  |  | BILL/00395/2024-2025 | BP-2024-25-287 | 25/09/2024 | 25/09/2024 | DIVISIONAL FOREST OFFICER | 2.7 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | RANGMOHAN PIPED WATER SUPPLY SCHEME | SM/15880 | New | SURFACE WATER BASED RANGMOHAN PWSS TO ACCOMODATE FHTC IN MIRIK BLOCK |  |  | ORD/000330/2022-2023 | 2669/NKWSMD | 01/03/2023 | 30/12/2024 | MAHENDRA ADHIKARI | 304.14 | 203.7 | 66.97 | 85
Total | [13 empty] | 307.9 | 203.7 | 66.16