## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE | SM/18534 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE | SM/18534 | New | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 5 Mouzas in Kurseong Block within Darjeeling District under Kurseong Division, P.H.E.D- GTA. |  |  | ORD/000267/2023-2024 | 100/NKWSMD | 15/01/2024 | 18/02/2026 | INTERIOR'S NEST | 2672.64 | 347.26 | 12.99 | 35
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE | SM/18534 | New | ADDITIONAL WORK FOR GROUND WATER RESERVOIR HAVING CAPACITY OF 20 ML AT DURPIN LAKE TO ACCOMMODATE 5 MOUZAS IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. |  |  | ORD/000058/2025-2026 | 826/NKWSMD | 09/06/2025 | 06/12/2025 | INTERIOR'S NEST | 318.4 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 6 mouzas in Kurseong Block within Darjeeling District under Kurseong Division, PHE DTE | SM/18534 | New | GRAVITY BASED WATER SUPPLYSCHEME FORGROUND WATER RESERVIOR HAVING CAPACITY OF 20ML AT DURPIN LAKE 2 UNDER JAL JEEVAN MISSION. |  |  | BILL/00721/2024-2025 | BP-2024-25-475 | 04/02/2025 | 04/02/2025 | DIVISIONAL FOREST OFFICER | 6.87 | 0 | 0 | 0
Total | [13 empty] | 3047.15 | 347.26 | 11.4