## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST | SM/18559 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 969/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 4.73 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST | SM/18559 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST | SM/18559 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SEPOYDHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST UNDER KURSEONG DIVISION, PHED-GTA |  |  | ORD/000046/2025-2026 | 634/NKWSMD | 05/05/2025 | 01/11/2025 | VAJRA ENTERPRISES | 59.3 | 0 | 0 | 95
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SEPOY DHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST | SM/18559 | New | SURFACE WATER BASED SEPOYDHURA (D.R.) TEA GARDEN, KHARIA BUSTY CHAITAPANI TEA GARDEN & BAMAN DHURA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK. | Assistant Engineer5 |  | ORD/000167/2023-2024 | 920/NKWSMD | 11/08/2023 | 17/05/2025 | SHAKTI CONSTRUCTION | 1345.85 | 938.77 | 69.75 | 50
Total | [13 empty] | 1459.13 | 938.77 | 64.34