## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE | SM/18588 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 970/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 8.04 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE | SM/18588 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00957/2023-2024 | BP-2023-24-657 | 23/03/2024 | 23/03/2024 | WBSEDCL | 11.34 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE | SM/18588 | New | SURFACE WATER BASED PURBA AND PASCHIM PHUGURI TEA GARDEN PHUGURI FOREST & ITS SURROUNDING VILLAGE PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE |  |  | ORD/000169/2023-2024 | 913/NKWSMD | 11/08/2023 | 06/02/2025 | INTERIOR'S NEST | 2568.72 | 617.7 | 24.05 | 75
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE | SM/18588 | New | ADDITIONAL WORK FOR SURFACE WATER BASED PURBA AND PASCHIM PHUGURI TEA GARDEN PHUGURI FOREST AND ITS SURROUNDING VILLAGE PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. |  |  | ORD/000059/2025-2026 | 829/NKWSMD | 09/06/2025 | 06/12/2025 | INTERIOR'S NEST | 93.84 | 0 | 0 | 0
5 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR PURBA & PASCHIM PHUGURI TEA GARDEN, PHUGURI FOREST & ITS SURROUNDING VILLAGE | SM/18588 | New | Balance work for Surface water based Purba & Paschim Phuguri Tea Garden Phuguri Forest and its Surrounding under Kurseong Division, P.H.E-GTA. |  |  | ORD/000057/2025-2026 | 874/NKWSMD | 16/06/2025 | 16/06/2026 | INTERIOR'S NEST | 312.15 | 0 | 0 | 0
Total | [13 empty] | 2994.09 | 617.7 | 20.63