## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. | SM/18638 | New | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 958/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 3.92 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. | SM/18638 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for North & South Tea Garden with FHTC under JJM/JSP. | SM/18638 | New | SURFACE WATER BASED NORTH & SOUTH SHIBKHOLA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSEONG BLOCK. |  |  | ORD/000162/2023-2024 | 910/NKWSMD | 11/08/2023 | 03/03/2025 | AROGYA ENTERPRISES | 1336.08 | 0 | 0 | 95
Total | [13 empty] | 1389.25 | 0 | 0