## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE | SM/18639 | New | SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE |  |  | ORD/000163/2023-2024 | 911/NKWSMD | 11/08/2023 | 10/08/2024 | INTERIOR'S NEST | 1516.55 | 547.67 | 36.11 | 65
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE | SM/18639 | New | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 960/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 11.68 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE | SM/18639 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00759/2023-2024 | BP-2023-24-504 | 26/02/2024 | 26/02/2024 | WBSEDCL | 7.09 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE | SM/18639 | New | ADITIONAL WORK FOR SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHED-GTA. |  |  | ORD/000061/2025-2026 | 830/NKWSMD | 09/06/2025 | 06/12/2025 | MAA DURGA ENTERPRISE | 54.17 | 0 | 0 | 0
5 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SINGBULLI TEA GARDEN, MANJUA FOREST & ITS SURROUNDING VILLAGE | SM/18639 | New | STRENGHTENING OF LAYING DISTRIBUTION SYSTEM FOR SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION,PHE.DTE. |  |  | ORD/000060/2025-2026 | 831/NKWSMD | 09/06/2025 | 06/12/2025 | INTERIOR'S NEST | 253.18 | 0 | 0 | 0
Total | [13 empty] | 1842.66 | 547.67 | 29.72