## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden | SM/18640 | New | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 959/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 5.46 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden | SM/18640 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Chattakpur Forest & Dayal Thong (D.R.) Tea Garden | SM/18640 | New | SURFACE WATER BASED CHATAKPUR AND DAYALTHONG PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000153/2023-2024 | 881/NKWSMD | 03/08/2023 | 07/08/2025 | GARGO TRADERS | 1197.13 | 0 | 0 | 95
Total | [13 empty] | 1251.84 | 0 | 0