## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) | SM/18647 | New | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 972/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 10.32 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) | SM/18647 | New | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 1 - Sonada Khasmahal part 1] |  |  | ORD/000171/2023-2024 | 915/NKWSMD | 11/08/2023 | 10/08/2024 | M/S. ASHOK KUMAR PERIWAL | 1177.68 | 0 | 0 | 80
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) | SM/18647 | New | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART) ,OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 2 - Sonada Khasmahal part 2] |  |  | ORD/000173/2023-2024 | 916/NKWSMD | 11/08/2023 | 07/04/2025 | M/S. ASHOK KUMAR PERIWAL | 1167.7 | 0 | 0 | 80
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART) & RINGTONG TEA GARDEN (PART) | SM/18647 | New | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART) ,OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 3 - Rongmook ceder (part), Oaks (part) & Ringtong tea garden (part)] |  |  | ORD/000174/2023-2024 | 917/NKWSMD | 11/08/2023 | 10/08/2024 | TIKARAM SHARMA | 1263.3 | 0 | 0 | 85
Total | [13 empty] | 3619 | 0 | 0