## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) | SM/18648 | New | SURFACE WATER BASED RANGMOOK CEDER TEA GARDEN (PART) AND OAKS TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN JOREBUNGLOW SUKHIAPOKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.DTE. |  |  | ORD/000164/2023-2024 | 912/NKWSMD | 11/08/2023 | 01/06/2026 | M/S. ASHOK KUMAR PERIWAL | 2166.21 | 253.29 | 11.69 | 80
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) | SM/18648 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 975/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 5.24 | 0 | 0 | 0
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR RONGMOOK CEDER TEA GARDEN (PART) & OKAS TEA GARDEN (PART) | SM/18648 | New | ADDITIONAL WORK FOR SURFACE WATER BASED RANGMOOK CEDER TEA GARDEN (PART) AND OAKS TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN JOREBUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E. DTE. |  |  | ORD/000358/2025-2026 | 834/NKWSMD | 09/06/2025 | 06/12/2025 | M/S. ASHOK KUMAR PERIWAL | 157.85 | 0 | 0 | 0
Total | [13 empty] | 2329.29 | 253.29 | 10.87