## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden | SM/18649 | New | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 967/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 2.14 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden | SM/18649 | New | FOREST PAYMENT |  |  | BILL/00760/2023-2024 |  | 15/02/2024 | 15/02/2024 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden | SM/18649 | New | FOREST PAYMENT |  |  | BILL/00905/2023-2024 | BP-2023-24-497 | 17/02/2024 | 17/02/2024 | DIVISIONAL FOREST OFFICER | 7.43 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden | SM/18649 | New | SURFACE WATER BASED TINDHARIA & NARBUNG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSOENG BLOCK. |  |  | ORD/000166/2023-2024 | 919/NKWSMD | 11/08/2023 | 07/04/2025 | SUNIT DEEP RAI | 1161.89 | 798.69 | 68.74 | 100
5 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Tindharia & Nurbang Tea Garden | SM/18649 | New | ADDITIONAL WORK FOR TINDHARIA & NORBUNG TEA GARDEN WATER SUPPLY SCHEME UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED. |  |  | ORD/000010/2025-2026 | 496/NKWSMD | 09/04/2025 | 08/07/2025 | SUNIT DEEP RAI | 17.57 | 0 | 0 | 0
Total | [13 empty] | 1199.75 | 798.69 | 66.57