## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS Scheme for Mirik Khasmahal | SM/18650 | New | SURFACE WATER BASED MIRIK KHASMAHAL (P) PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. |  |  | ORD/000165/2023-2024 | 918/NKWSMD | 11/08/2023 | 10/08/2024 | SHAKTI CONSTRUCTION | 1224.81 | 709.41 | 57.92 | 90
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS Scheme for Mirik Khasmahal | SM/18650 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 973/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 8.04 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PWS Scheme for Mirik Khasmahal | SM/18650 | New | PAYMENT FOR WBSEDCL |  |  | BILL/00956/2023-2024 | BP-2023-24-658 | 23/03/2024 | 23/03/2024 | WBSEDCL | 12.27 | 0 | 0 | 0
Total | [13 empty] | 1245.13 | 709.41 | 56.97