## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN | SM/18651 | New | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 971/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 7.21 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN | SM/18651 | New | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. |  |  | BILL/00280/2024-2025 | BP-2024-25-220 | 28/08/2024 | 28/08/2024 | WBSEDCL | 5.43 | 0 | 0 | 0
3 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN | SM/18651 | New | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. |  |  | BILL/00096/2024-2025 | BP-2024-25-88 | 08/07/2024 | 08/07/2024 | WBSEDCL | 17.08 | 0 | 0 | 0
4 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN | SM/18651 | New | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. |  |  | ORD/000168/2023-2024 | 921/NKWSMD | 11/08/2023 | 10/08/2024 | SHAKTI CONSTRUCTION | 1126.3 | 0 | 0 | 90
5 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR MARMA TEA GARDEN | SM/18651 | New | ADDITIONAL WORK FOR SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK P.H.E-GTA. |  |  | ORD/000030/2025-2026 | 639/NKWSMD | 05/05/2025 | 01/11/2025 | SHAKTI CONSTRUCTION | 87.36 | 0 | 0 | 0
Total | [13 empty] | 1243.37 | 0 | 0