## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. | SM/18652 | New | SURFACE WATER BASED SINGEL TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK. |  |  | ORD/000172/2023-2024 | 914/NKWSMD | 11/08/2023 | 03/11/2025 | M/S. ASHOK KUMAR PERIWAL | 958.42 | 133.38 | 13.92 | 85
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. | SM/18652 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 968/NKWSMD | 21/08/2023 | 21/08/2023 | Resource Division | 6.15 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Singel Tea Garden with FHTC under JJM/JSP. | SM/18652 | New | ADDITIONAL WORK FOR SINGEL TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT-DARJEELING KURSEONG DIVISION, P.H.E.D-GTA. |  |  | ORD/000190/2025-2026 | 860/NKWSMD | 13/06/2025 | 10/12/2025 | SHRI SHYAM ENGINEERING | 195.38 | 0 | 0 | 0
Total | [13 empty] | 1159.94 | 133.38 | 11.5