## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Edenvale Tea Garden | SM/18710 | New | SURFACE WATER BASED EDENVALE TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000160/2023-2024 | 894/NKWSMD | 07/08/2023 | 03/02/2024 | YAMA CONSTRUCTIONS LLP | 139.48 | 114.86 | 82.35 | 50
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS Scheme for Edenvale Tea Garden | SM/18710 | New | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 1298/NKWSMD | 30/10/2023 | 30/10/2023 | Resource Division | 0.67 | 0 | 0 | 0
Total | [13 empty] | 140.15 | 114.86 | 81.96