## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. | SM/18723 | New | Augmentation of Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme, Block: Kurseong, District: Darjeeling. |  |  | ORD/000014/2024-2025 | 979/NKWSMD | 18/06/2024 | 17/08/2024 | SUNRISE ENTERPRISES | 24.35 | 0 | 0 | 100
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. | SM/18723 | New | Ground Water Reservoir of 20 ML At Sepoydhura Near Woodcut Under Kurseong Division, P.H.E.D-GTA. |  |  | ORD/000227/2023-2024 | 1288/NKWSMD | 17/10/2023 | 02/05/2026 | INTERIOR'S NEST | 2445.49 | 143.28 | 5.86 | 35
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | SOURCE AND CONSTRUCTION OF OPEN GROUND WATER RESERVOIR OF CAPACITY 20 ML AT SEPOYDHURA (NEAR WOODCOT) UNDER KURESONG BLOCK WITHIN DARJEEING DISTRICT UNDER KURSEONG DIVISION, DTE. | SM/18723 | New | Augmentation for ground water Reservoir of capacity 20 ML at Sepoydhura (Near Woodcut) Kurseong under PHED, Kusseong Sub- Division, GTA. |  |  | ORD/000056/2025-2026 | 824/NKWSMD | 09/06/2025 | 09/06/2026 | INTERIOR'S NEST | 411.05 | 0 | 0 | 0
Total | [13 empty] | 2880.89 | 143.28 | 4.97