## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD | SM/18727 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 998/NKWSMD | 24/08/2023 | 24/08/2023 | Resource Division | 10.36 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RANGBUL & HILL CART ROAD | SM/18727 | New | RUNGBUL & HILL CART ROAD PIPED WATER SUPPLY SCHEME UNDER KURSEONG DIVISION. |  |  | ORD/000189/2023-2024 | 987/NKWSMD | 23/08/2023 | 16/09/2025 | GARGO TRADERS | 1927.74 | 1379.15 | 71.54 | 100
Total | [13 empty] | 1938.1 | 1379.15 | 71.16