## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) | SM/18730 | New | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 1285/NKWSMD | 17/10/2023 | 17/10/2023 | Resource Division | 6.92 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) | SM/18730 | New | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-I) (MARGARET HOPE) |  |  | ORD/000218/2023-2024 | 1207/NKWSMD | 10/10/2023 | 09/10/2024 | M/S. ASHOK KUMAR PERIWAL | 1076.48 | 0 | 0 | 90
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) | SM/18730 | New | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Margaret Hope), Part of Ringtong Tea Garden (Gunawar) & Nahori Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-II) (MARGARET HOPE) |  |  | ORD/000224/2023-2024 | 1286/NKWSMD | 17/10/2023 | 16/10/2024 | M/S. ASHOK KUMAR PERIWAL | 1084.55 | 0 | 0 | 80
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | PIPED WATER SUPPLY SCHEME WITH FHTC FOR RING TONG TEA GARDEN (MARGARET HOPE), PART OF RING TONG TEA GARDEN (GUNAWAR) & NAHORI TEA GARDEN (BALASON) | SM/18730 | New | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Margaret Hope), Part of Ringtong Tea Garden (Gunawar) & Nahori Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-III) |  |  | ORD/000225/2023-2024 | 1287/NKWSMD | 17/10/2023 | 16/10/2024 | TIKARAM SHARMA | 973.97 | 0 | 0 | 85
Total | [13 empty] | 3141.92 | 0 | 0