## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Augmentation of Nipania Piped Water Supply Scheme. | SM/18881 | Augmentation | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 18/09/2025 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 0 | 30
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Augmentation of Nipania Piped Water Supply Scheme. | SM/18881 | Augmentation | Augmentation of 4 nos of pipe water supply scheme within Darjeeling District under Kurseong Division. |  |  | BILL/00056/2025-2026 | 197/NK/C/W/WBSE | 25/09/2025 | 25/09/2025 | WBSEDCL | 16.36 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Augmentation of Nipania Piped Water Supply Scheme. | SM/18881 | Augmentation | Augmentation of 4 nos of pipe water supply scheme within Darjeeling District under Kurseong Division. |  |  | BILL/00055/2025-2026 | 196/NK/C/W/WBSE | 25/09/2025 | 25/09/2025 | WBSEDCL | 0.64 | 0 | 0 | 0
Total | [13 empty] | 602.79 | 0 | 0