## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA | SM/18917 | New | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 25/10/2024 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 0 | 80
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWS SCHEME FOR LEFT OUT HOUSEHOLD UNDER DIFFERENT VILLAGES OF KURSEONG BLOCK UNDER KURSEONG DIVISION PHED GTA | SM/18917 | New | WATER SUPPLY SCHEME FOR MALDIRAM FOREST PART, ST MARYS PART, UPPER LANKU & UPPER ROLAK PART, SIMRING TEA GARDEN PART, CHANDU BUSTY GIDHE PAHAR PART PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000108/2024-2025 | 1746/NKWSMD | 19/09/2024 | 19/09/2025 | DAJUBHAI CONSTRUCTION | 861.59 | 0 | 0 | 80
Total | [13 empty] | 1041.28 | 0 | 0