## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED | SM/19038 | New | SURFACE WATER BASED FOR MANGPUU CINCHONA PLANTATION PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E. DTE. |  |  | ORD/000249/2023-2024 | 3/NKWSMD | 03/01/2024 | 02/04/2025 | YAMA CONSTRUCTIONS LLP | 5612.47 | 4891.31 | 87.15 | 95
2 | DARJEELING | Rangli Rangliot | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Mangpuu Cinchona Plantation (for covering left out household) under Kurseong Division, PHED | SM/19038 | New | ADDITIONAL WORK FOR SURFACE WATER BASED FOR MANGPUU CINCHONA PLANTATION PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION P.H.E DTE. |  |  | ORD/000145/2024-2025 | 2347/NKWSMD | 19/12/2024 | 19/12/2025 | YAMA CONSTRUCTIONS LLP | 1156.69 | 633.72 | 54.79 | 75
Total | [13 empty] | 6769.16 | 5525.03 | 81.62