## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of AMBARI T. G. piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000092/2020-2021 | 1279/JD | 18/11/2020 | 18/12/2020 | NEW KUNDU ENTERPRISE | 14.38 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of AMBARI T. G. piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000091/2020-2021 | 1278/JD | 18/11/2020 | 17/01/2021 | SANDIP BANIK | 28.51 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | PROVIDING FHTC AT AMBARI T.G PWSS |  |  | VCH/001213/2020-2021 | 1123 | 22/01/2021 |  | SANDIP BANIK | 28.5 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | Providing FHTC Ambari TG Part D |  |  | VCH/001214/2020-2021 | 1124 | 22/01/2021 |  | NEW KUNDU ENTERPRISE | 11.95 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | PROVIDING FHTC FOR AMBARI T.G PWSS |  |  | VCH/001128/2020-2021 | 1077 | 14/01/2021 |  | SAHA CONSTRUCTION | 4.03 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | PRIVIDING FHTC AT AMBARI T.G PWWSS |  |  | VCH/001194/2020-2021 | 919 | 04/01/2021 |  | SANDIP BANIK | 4.21 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | Retrofitting works & other ancillary works related to FHTC at different places of Ambari TG PWSS.under Jalpaiguri Division P.H.E. Dte. |  |  | VCH/001485/2020-2021 | 1589 | 23/04/2021 |  | SANDIP BANIK | 1.82 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | RETROFITTING WORK & OTHER ANCILLARY WORK RELATED FHTC FOR AMBARI T.G PWSS |  |  | VCH/001795/2020-2021 | 1589 | 21/03/2021 |  | SANDIP BANIK | 1.82 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | LDS FOR PURBA DURAMARI PWSS |  |  | VCH/000045/2021-2022 | 08 | 07/05/2021 |  | SANJIT SAHA | 8.91 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Ambari Tea Garden Piped Water Supply Scheme | SM/06837 | Retrofitting | FHTC SADAR BLOCK ZONE II |  |  | VCH/001345/2021-2022 | BP-2021-22- 412 | 23/03/2022 |  | BISWAJIT BHADURI | 4.92 | 0 | 0 | 0
Total | [13 empty] | 109.04 | 0 | 0