## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Boalmari Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000151/2020-2021 | 475/RWS | 15/10/2020 | 14/11/2020 | KABYA ENTERPRISE | 4.7 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of BOALMARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) |  | Junior Engineer | ORD/000173/2020-2021 | 1105/JD | 20/10/2020 | 18/01/2021 | UMWEL ENGINEER PRIVATE LIMITED | 39.23 | 5.96 | 15.2 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | PROVIDING FHTC UNDER BOALMARI PWSS |  |  | VCH/001250/2020-2021 | 1205 | 04/02/2021 |  | KABYA ENTERPRISE | 4.23 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | PROVIDING FHTC FOR BOALMARI PWSS |  |  | VCH/001312/2020-2021 | 1302 | 11/02/2021 |  | UMWELT ENGINEER PRIVATE LIMITED | 29.94 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | RETROFITTING WORK FOR FHTC AT BOALMARI PWSS |  |  | VCH/001785/2020-2021 | 1565 | 19/03/2021 |  | UMWELT ENGINEER PRIVATE LIMITED | 4 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | FHTC BOALMARI |  |  | VCH/000327/2021-2022 | null | 01/10/2021 |  | KANAI LAL SEN | 22.04 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | Retrofitting Boalmari WSS |  |  | VCH/000465/2021-2022 | null | 26/10/2021 |  | KANAI LAL SEN | 4.78 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | Providing house connection under Boalmari Water Supply Scheme at Sadar Block under Jalpaiguri Division P.H.E.Dte. |  |  | ORD/000486/2021-2022 | 296/RWS | 20/04/2021 | 05/05/2021 | DEBABRATA GHOSH | 4.44 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Boalmari Piped Water Supply Scheme | SM/06838 | Retrofitting | Providing functional household tap connection (FHTC) with Jalsapna including Retrofitting works under the command area of Boalmari W/S/S under Jalpaiguri Division P.H.E. Dte.(Part ¿ F) |  |  | ORD/000571/2021-2022 | 182/RWS | 04/03/2022 | 19/03/2022 | KANAI LAL SEN | 4.51 | 0 | 0 | 0
Total | [13 empty] | 117.86 | 5.96 | 5.06