## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KAJALDIGI piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-C). |  | Junior Engineer | ORD/000088/2020-2021 | 1276/JD | 18/11/2020 | 16/02/2021 | NISHITH RANJAN KARMAKAR | 39.12 | 39.1 | 99.96 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Kajaldigi Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000106/2020-2021 | 442/RWS | 09/10/2020 | 08/11/2020 | M/S.PAMPA CONSTRACTION | 4.73 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | PROVIDING HOUSE CONNECYTION AT KAJALDIGHI PWSS |  |  | VCH/001152/2020-2021 | 1055 | 11/01/2021 |  | R.S CONSTRUCTION | 4.44 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | PROVIDING FHTC FOR KAJALDIGHI PWSS |  |  | VCH/001147/2020-2021 | 1100 | 22/01/2021 |  | M/S.PAMPA CONSTRACTION | 4.71 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Kajaldighi piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000059/2021-2022 | 1085/JD | 05/07/2021 | 25/07/2021 | GOUTAM DAS | 10.27 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | fhtc jiti |  |  | VCH/000347/2021-2022 | null | 05/10/2021 |  | CALCON CONSTRUCTIONS | 17.1 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | FHTC KAJALDIGHI |  |  | VCH/000909/2021-2022 | BP-2021-22-131 | 14/12/2021 |  | R.S CONSTRUCTION | 4.71 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | FHTC KAJAL DIGHI |  |  | VCH/000906/2021-2022 | BP-2021-22-133 | 14/12/2021 |  | PRAHLAD PRASAD SAHA | 4.83 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | FHTC LATAGURI, MOULANI, KRANTI GP |  |  | VCH/001298/2021-2022 | BP-2021-22-467 | 28/03/2022 |  | SAHA CONSTRUCTION | 2.2 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | Parmanent work of Bhatiapara pipe water supply scheme damage by heavy near swanghat bridge and Fotoktari bridge within Salbari -I G.P. under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/000235/2017-2018 | 556/JSSD | 23/03/2018 | 22/04/2018 | RABINDRANATH DUTTA | 3.1 | 2.27 | 73.22 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Kajaldighi Piped Water Supply Scheme | SM/06839 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Kajaldighi piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-D). |  | Junior Engineer | ORD/000398/2020-2021 | 74/RWS | 19/02/2021 | 06/03/2021 | R.S CONSTRUCTION | 4.76 | 4.75 | 99.9 | 0
Total | [13 empty] | 99.96 | 46.13 | 46.15