## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIGORALBARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) |  | Junior Engineer | ORD/000083/2020-2021 | 1268/JD | 18/11/2020 | 16/02/2021 | NARAYAN CHAKRABORTY | 36.96 | 30.12 | 81.49 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argi Goralbari piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000183/2020-2021 | 1498/JD | 22/12/2020 | 21/01/2021 | BISWAJIT BHADURI | 17.51 | 6.58 | 37.58 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | Providing FHTC under Arji Garalbari |  |  | VCH/001150/2020-2021 | 1050 | 11/01/2021 |  | ABHIJIT SARKAR | 4.72 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | Providing Functional House hold tap Connection (FHTC)in connection with Jaldhara/ Jalsapna a t Arji Goralbari piped W/S/S within Jalpaiguri Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ H) |  | Junior Engineer | ORD/000180/2021-2022 | 685/RWS | 27/09/2021 | 12/10/2021 | NARAYAN CHAKRABORTY | 4.25 | 0 | 0 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | Providing Functional House hold tap Connection(FHTC) In connection with Jaldhara/ Jalsapna at Arji Goralbari piped W/S/S within Jalpaiguri Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ G) |  | Junior Engineer | ORD/000178/2021-2022 | 683/RWS | 27/09/2021 | 12/10/2021 | BISWAJIT BHADURI | 3.4 | 0 | 0 | 1
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | Reparing & renovation of Boundary wall, approach At H/W site for Goralbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000212/2021-2022 | 699/RWS | 27/09/2021 | 27/10/2021 | ASIT PAUL | 4.84 | 0 | 0 | 1
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | Retrofitting works related to FHTC at Kamar para, Taltala line , Purba Madati para, Purba Kamar Para for Argi Garalbari . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000273/2021-2022 | 817/RWS | 30/11/2021 | 10/12/2021 | BISWAJIT BHADURI | 4.85 | 0 | 0 | 1
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | ARAGI GORALBARI |  |  | VCH/001082/2021-2022 | BP-2021-22-171 | 14/01/2022 |  | NARAYAN CHAKRABORTY | 3.47 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | FHTC PURBAMAGUR MARI PWSS |  |  | VCH/001313/2021-2022 | BP-2021-22-335 | 03/03/2022 |  | MONOJ GHOSH | 7.74 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | FHTC NAYASAILYA T.G PWSS |  |  | VCH/001314/2021-2022 | BP-2021-22-336 | 03/03/2022 |  | GAP ENGINEERS ENTERPRISES | 12.52 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | FHTC ENGO T.G PWSS |  |  | VCH/001327/2021-2022 | BP-2021-22-464 | 27/03/2022 |  | NABIN PRODHAN | 2.26 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | FHTC PURBAMAGURMARI PWSS |  |  | VCH/001312/2021-2022 | BP-2021-22-334 | 03/03/2022 |  | ARATI CONSTRUCTION | 7.42 | 0 | 0 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Aragi Goralbari Piped Water Supply Scheme | SM/06840 | Retrofitting | Construction of Pump House (3.60 M X 2.40 M ) Size With Sanitary & Plumbing Arrangement of Rejuvenation Garalbari . W/S/S ( zone - I ) 3rd T/W site under Jalpaiguri Division , P.H.E. Dte. |  | Junior Engineer | ORD/000318/2021-2022 | 869/RWS | 08/12/2021 | 07/01/2022 | ABHIJIT SARKAR | 4.65 | 4.65 | 100 | 0
Total | [13 empty] | 114.59 | 41.35 | 36.09