## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme | SM/06842 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NAKHATI T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte |  | Junior Engineer | ORD/000163/2020-2021 | 1118/JD | 02/11/2020 | 01/01/2021 | R.S CONSTRUCTION | 38.19 | 20.56 | 53.83 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Funtional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna including existing LDS under the comand area of Nakhati Tea Garden Piped Water Supply Scheme | SM/06842 | Retrofitting | fhtc nakhati |  |  | VCH/000351/2021-2022 |  | 05/10/2021 | 05/10/2021 | R.S CONSTRUCTION | 10 | 0 | 0 | 0
Total | [13 empty] | 48.19 | 20.56 | 42.66