## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme | SM/06845 | Retrofitting | PROVIDING FHTC FOR BHANGAMALI PWSS |  |  | VCH/001333/2020-2021 | 1195 | 04/02/2021 |  | MRINMOY KANTI DUTTA | 14.66 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme | SM/06845 | Retrofitting | BHANGAMALI |  |  | VCH/001052/2021-2022 | BP-2021-22-203 | 19/01/2022 |  | MRINMOY KANTI DUTTA | 14.38 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme | SM/06845 | Retrofitting | Retrofitting works in connection with FHTC works along with PWD road from Prodhan Para to Putimari and different places at Bhangamali under Bhangamali Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000569/2021-2022 | 1811/JD | 18/11/2021 | 03/12/2021 | RABINDRANATH DUTTA | 17.81 | 0.05 | 0.26 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Bhangamali Piped Water Supply Scheme | SM/06845 | Retrofitting | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) | Assistant Engineer | Junior Engineer | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 09/07/2023 | RAKESH SARKAR | 1.76 | 0.35 | 19.81 | 0.5
Total | [13 empty] | 48.61 | 0.4 | 0.82