## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | SM/06846 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of YOUNGTONG T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte |  | Junior Engineer | ORD/000161/2020-2021 | 1080/JD | 15/10/2020 | 29/11/2020 | ASHIT KUMAR SINGHA | 26.73 | 17.81 | 66.62 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | SM/06846 | Retrofitting | PROVIDING FHTC AT YOUNGTONG T.G PWSS |  |  | VCH/001154/2020-2021 | 1102 | 22/01/2021 | 22/01/2021 | M/S.PAMPA CONSTRACTION | 4.49 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | SM/06846 | Retrofitting | iep for young tong t.g pwss |  |  | VCH/000377/2021-2022 | 291 | 05/09/2021 | 05/09/2021 | ASHIT KUMAR SINGHA | 3.74 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | SM/06846 | Retrofitting | ADDITIONAL LDS FOR YOUNGTONG T.G PWSS |  |  | VCH/000549/2021-2022 | 338/21-22 | 01/10/2021 | 01/10/2021 | M/S PAMPA CONSTRUCTION | 0.75 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | SM/06846 | Retrofitting | supply stesonarry |  |  | VCH/000541/2022-2023 | BP-2021-23-169 | 29/09/2022 | 29/09/2022 | NEW KUNDU ENTERPRISE | 0.03 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | SM/06846 | Retrofitting | fhtc mohit nagar |  |  | VCH/000526/2022-2023 | BP-2021-22-168 | 29/09/2022 | 29/09/2022 | M/S DEY & ROY CHOUDHURY | 1.14 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | SM/06846 | Retrofitting | Retrofitting work of pipeline at Yongtong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division. P.H.E.Dte.(Phase-I) |  | Junior Engineer | ORD/000033/2021-2022 | 07/JSSD | 13/04/2021 | 03/05/2021 | R.S CONSTRUCTION | 4.13 | 4.12 | 99.66 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Youngtong Tea Garden Piped Water Supply Scheme | SM/06846 | Retrofitting | Retrofitting work of pipeline at Yongtong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte.(Phase-II). |  |  | ORD/000034/2021-2022 | 09/JSSD | 13/04/2021 | 03/05/2021 | M/S PAMPA CONSTRUCTION | 3.52 | 3.5 | 99.62 | 0
Total | [13 empty] | 44.53 | 25.43 | 57.11