## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Argimaria Kamalapokori Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000166/2020-2021 | 469/RWS | 15/10/2020 | 14/11/2020 | PINTU DAS | 4.73 | 0 | 0 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000186/2020-2021 | 1494/JD | 22/12/2020 | 05/02/2021 | R.S CONSTRUCTION | 23.66 | 0 | 0 | 1
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000200/2020-2021 | 1536/JD | 31/12/2020 | 30/01/2021 | PRADIP SAHA | 15.67 | 15.6 | 99.52 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-D) |  | Junior Engineer | ORD/000193/2020-2021 | 1545/JD | 31/12/2020 | 14/02/2021 | R.S CONSTRUCTION | 28.69 | 28.94 | 100.88 | 1
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | PROVIDING FHTC ARGIMARIA KAMLAPUKHURI PWSS |  |  | VCH/001251/2020-2021 | 1206 | 04/02/2021 |  | PINTU DAS | 4.85 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | PROVIDING FHTC FOR ARJIMARIA KAMLAPUKURI PWSS |  |  | VCH/000039/2021-2022 | 39 | 21/05/2021 |  | R.S CONSTRUCTION | 23.9 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Retrofitting works related to FHTC for Arjimaria Kamlapukari WSS under Jalpaiguri Div. PHE Dte. |  |  | VCH/000408/2021-2022 | 353/21-22 | 15/09/2021 |  | R.S CONSTRUCTION | 4.25 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Retrofitting works at related to FHTC for Arjimaria Kamalapukuri Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000434/2020-2021 | 67/RWS | 12/02/2021 | 22/02/2021 | R.S CONSTRUCTION | 4.17 | 0 | 0 | 1
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | providing FHTC for arajimaria Kamla Pukhari |  |  | VCH/001171/2021-2022 | BP-2021-22-238 | 23/02/2022 |  | R.S CONSTRUCTION | 4.94 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIMARIA KAMOLAPOKORI piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000639/2020-2021 | 19/JD | 14/01/2021 | 15/03/2021 | BILTU DAS | 36.92 | 0 | 0 | 1
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at balance portion of Arjimaria Kamalapokhori W/S Scheme in connection with JJM under Jalpaiguri Division, PHE Dte (Part-G). | Assistant Engineer | Junior Engineer | ORD/000138/2023-2024 | 707/JD | 13/07/2023 | 12/08/2023 | M/S R.K SINGHA & SONS | 30.55 | 0 | 0 | 90
12 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna including retrofitting of existing LDS under the command area of Dabgram-II piped Water Supply Scheme (South Zone) at Rajganj Block under Jalpaiguri Division, PHE Dte. Phase-I | Assistant Engineer,HQ | Junior Engineer | ORD/000141/2020-2021 | 1250/JD | 11/11/2020 | 02/12/2020 | ASIM GUPTA . | 4.32 | 3.04 | 70.53 | 0
13 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Arjimaria Kamlapukuri Piped Water Supply Scheme | SM/06936 | Retrofitting | Repairing of Pipe Line With Other allied works related to Pipeline Under Luksaan Bazaar water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  |  | ORD/000392/2020-2021 | 612/JSSD | 18/02/2021 | 10/03/2021 | MONOTOSH ROY | 4.9 | 4.86 | 99.08 | 0
Total | [13 empty] | 191.57 | 52.44 | 27.38