## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Chrarbari Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000107/2020-2021 | 466/RWS | 15/10/2020 | 14/11/2020 | M/S.DEY & ROY CHOUDHURY | 4.71 | 8.84 | 187.75 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHARERBARI piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000112/2020-2021 | 1284/JD | 18/11/2020 | 02/01/2021 | RAGHU DAS | 15.22 | 14.94 | 98.13 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Charerbari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-D) |  | Junior Engineer | ORD/000192/2020-2021 | 1552/JD | 31/12/2020 | 14/02/2021 | NEW KUNDU ENTERPRISE | 27.7 | 55.03 | 198.67 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | providing fhtc for charer bari pwss |  |  | VCH/000316/2021-2022 |  | 01/10/2021 | 01/10/2021 | NEW KUNDU ENTERPRISE | 2.02 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | FHTC CHARERBARI WSS |  |  | VCH/001295/2021-2022 | BP-2021-22-415 | 23/03/2022 | 23/03/2022 | NEW KUNDU ENTERPRISE | 4.16 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | FHTC DWARIKAMARI |  |  | VCH/001362/2021-2022 | BP-2021-22-524 | 30/03/2022 | 30/03/2022 | SUBRATA GOSWAMI | 8.41 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHRERBARI piped Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000222/2020-2021 | 100/JD | 18/01/2021 | 04/03/2021 | SANKAR DAS | 21.16 | 19.59 | 92.6 | 100
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna for providing drinking water under the command area of Charerbari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000328/2020-2021 | 222/JD | 12/02/2021 | 29/03/2021 | M/S DEY & ROY CHOUDHURY | 24.4 | 11.28 | 46.22 | 40
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | Restoration work in connection with FHTC works for the habitation of Bideshi Para,Chobarbari, Thonthonerbari and Dakshin Ghutkara under Charerbari W/S/S under Jalpaiguri Division , P.H.E. Dte |  |  | ORD/000530/2021-2022 | 176/RWS | 03/03/2022 | 18/03/2022 | NEW KUNDU ENTERPRISE | 4.16 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHRERBARI piped Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. (Part-F) |  | Junior Engineer | ORD/000227/2020-2021 | 91/JD | 14/01/2021 | 28/02/2021 | KAMALESH SEN | 20.95 | 20.58 | 98.19 | 100
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Charerbari Piped Water Supply Scheme | SM/06937 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with under the command area of Charerbari Water Supply Scheme at Managuri Block under Jalpaiguri Division, P.H.E. Dte. (PHASE - G) |  |  | ORD/000285/2022-2023 | 650/RWS | 21/10/2022 | 10/11/2022 | NEW KUNDU ENTERPRISE | 2.42 | 1.83 | 75.48 | 100
Total | [13 empty] | 135.33 | 132.08 | 97.6