## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Madabdanga Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000168/2020-2021 | 471/RWS | 15/10/2020 | 14/11/2020 | ALICK DUTTA | 4.72 | 9.48 | 200.87 | 1
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Madabdanga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000211/2020-2021 | 48/JD | 07/01/2021 | 08/03/2021 | M/S SIBU DEY AND CO. | 39.4 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Madab danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000202/2020-2021 | 1537/JD | 31/12/2020 | 01/03/2021 | ANUP SARKAR | 32.76 | 59.31 | 181.08 | 1
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | PROVIDING FHTC AT MADHABDANGA PWSS |  |  | VCH/001156/2020-2021 | 1054 | 11/01/2021 | 11/01/2021 | BHOWMIK ENTERPRISES | 4.41 | 0 | 0 | 0
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | PROVIDING FHTC FOR JURANTI T.G PWSS |  |  | VCH/000336/2021-2022 |  | 04/10/2021 | 04/10/2021 | NARAYAN CH SAHA & SONS | 18.42 | 0 | 0 | 0
6 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | FHTC MADHAB DANFGA |  |  | VCH/001179/2021-2022 | BP-2021-22-234 | 23/02/2022 | 23/02/2022 | ANUP SARKAR | 3.99 | 0 | 0 | 0
7 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | CONST SULICE VALVE CHEMBER FOR DAKSHIN SHALBARI PWSS |  |  | VCH/001248/2021-2022 | BP-2021-22-389 | 17/03/2022 | 17/03/2022 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0 | 0
8 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | RETROFITTING WORK MADHAB DANGA PWSS |  |  | VCH/001257/2021-2022 | BP-2021-22-405 | 23/03/2022 | 23/03/2022 | ANUP SARKAR | 2.25 | 0 | 0 | 0
9 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | CONST. SLUICE VALVE DAKSHIN SALBARI |  |  | VCH/001320/2021-2022 | BP-2021-22-389 | 17/03/2022 | 17/03/2022 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0 | 0
10 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | FHTC MADHYA KHUTTIMARI |  |  | VCH/001326/2021-2022 | BP-2021-22-369 | 16/03/2022 | 16/03/2022 | ALOKE DEY | 16.81 | 0 | 0 | 0
11 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | Construction of store below OHR , plinth protection and construction of valve chamber etc. including through reparing of pipe line with cleaning to provide water facility near Jalpesh more under Madhabdanga W/S/S under Jalpaiguri Division , P.H.E. Dte |  |  | ORD/000319/2021-2022 | 870/RWS | 08/12/2021 | 23/12/2021 | M/S SURAJIT DEY AND CO. | 4.85 | 0 | 0 | 0
12 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Madhabdanga Piped Water Supply Scheme | SM/06938 | Retrofitting | Retrofitting works in connection with FHTC at Kadamtala, Indira More and Baman para under Madhabdanga W/S/S under Jalpaiguri Division , P.H.E. Dte |  |  | ORD/000395/2021-2022 | 849/RWS | 03/12/2021 | 13/12/2021 | ANUP SARKAR | 2.25 | 0 | 0 | 0
Total | [13 empty] | 139.5 | 68.79 | 49.31