## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06952 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000215/2020-2021 | 1549/JD | 31/12/2020 | 01/03/2021 | CALCON CONSTRUCTIONS | 40.32 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06952 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000250/2020-2021 | 563/JSSD | 01/02/2021 | 16/02/2021 | NARAYAN CHANDRA ADHIKARY | 4.44 | 4.43 | 99.61 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Jiti Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06952 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000216/2020-2021 | 1550/JD | 31/12/2020 | 30/01/2021 | PARAMJYOTI ENTERPRISE | 12.27 | 12.26 | 99.89 | 1
Total | [13 empty] | 57.03 | 16.68 | 29.25