## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | SM/06953 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Hope T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000220/2020-2021 | 30/JD | 05/01/2021 | 21/03/2021 | UMWELT ENGINEER PRIVATE LIMITED | 43.55 | 0 | 0 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | SM/06953 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Bhangarhat piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000056/2021-2022 | 1076/JD | 02/07/2021 | 01/08/2021 | DIPANKAR DUTTA | 24.38 | 46.35 | 190.16 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | SM/06953 | Retrofitting | FHTC FOR BHANGARHAT PWSS |  |  | VCH/000367/2021-2022 | 376/21-22 | 20/09/2021 | 20/09/2021 | MRINMOY KANTI DUTTA | 23.75 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Hope Tea Garden Area Piped Water Supply Scheme at Nagrakata Block | SM/06953 | Retrofitting | fuel bill |  |  | BILL/00030/2023-2024 | BP-2023-24-30 | 12/04/2023 | 12/04/2023 | FILL & SMILE | 1.9 | 0 | 0 | 0
Total | [13 empty] | 93.58 | 46.35 | 49.53