## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06954 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Caron T.G. area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000213/2020-2021 | 1548/JD | 31/12/2020 | 14/02/2021 | SANDIP BANIK | 28.61 | 57.21 | 199.99 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Caron Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06954 | Retrofitting | Emergency repairing of existing pipelines at different locations damaged due to road development works including cleaning chokages of blocked pipelines for smooth running of drinking water under Paschim Salbari (zone-I) water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 558/RWS | 01/09/2022 | 01/10/2022 | SAHA CONSTRUCTION | 3.5 | 3.49 | 99.91 | 1
Total | [13 empty] | 32.11 | 60.71 | 189.09