## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06955 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Lukshan T.G. area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000214/2020-2021 | 1547/JD | 31/12/2020 | 16/03/2021 | SCEC BOENTER KDAS JOINT VENTURE | 42.4 | 19.16 | 45.19 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06955 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Lukshan T.G. area PWSS at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000341/2020-2021 | 566/JSSD | 01/02/2021 | 16/02/2021 | ALICK DUTTA | 4.61 | 0 | 0 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06955 | Retrofitting | RETROFITTING WORK FOR FHTC FOR JABRAMALI PWSS |  |  | VCH/000121/2021-2022 | 124/21-22 | 07/07/2021 |  | M/S RATAN KUMAR DAS GUPTA AND CO | 13.89 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Luksan Bazar Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06955 | Retrofitting | ADD BILL |  |  | VCH/000769/2021-2022 | 536/21-22 | 17/11/2021 |  | GENESIS ADVERTISING PVT LTD | 2.89 | 0 | 0 | 0
Total | [13 empty] | 63.79 | 19.16 | 30.03