## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Nayasaily T.G. area PWSS at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000245/2020-2021 | 560/JSSD | 01/02/2021 | 16/02/2021 | PRIYABRATA KARMAKAR | 4.84 | 4.83 | 99.88 | 0
2 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Nayasailya T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000219/2020-2021 | 13/JD | 04/01/2021 | 18/02/2021 | GOUTAM DAS | 26.22 | 26.12 | 99.63 | 0
3 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06956 | Retrofitting | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | Assistant Engineer | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 14/07/2023 | APIKUL ALI | 1.76 | 0 | 0 | 0
4 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NAYASAILYA T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,Assistant Engineer,HQ | Junior Engineer | ORD/000032/2021-2022 | 752/JD | 13/05/2021 | 08/08/2024 | GAP ENGINEERS ENTERPRISE | 22.63 | 0 | 0 | 90
5 | JALPAIGURI |  | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Sapna for Nayasaily Tea Garden Piped Water Supply Scheme at Nagrakata Block | SM/06956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of GORALBARI (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-A) |  | Junior Engineer | ORD/000223/2020-2021 | 94/JD | 14/01/2021 | 28/02/2021 | SAPTASWA SARKAR | 28 | 16.59 | 59.25 | 0
Total | [13 empty] | 83.46 | 47.55 | 56.97